## Index
Workbook Index and Navigation
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Every sheet, the register it is generated from, and the record count it currently holds. The repository under programme/registry is the source of truth; this workbook is a generated view.
# | Sheet | Group | Register | Records
1 | Index | Management
2 | Executive Dashboard | Management
3 | Programme Dashboard | Management
4 | Master Tracker | Delivery | tasks
5 | Gantt | Delivery | tasks
6 | Milestones | Delivery | milestones
7 | Phases | Delivery | phases
8 | Deliverables | Delivery | deliverables
9 | Dependencies | Delivery | dependencies
10 | RAID | Governance | raid
11 | Decision Log | Governance | decisions
12 | Change Requests | Governance | change_requests
13 | RACI | Governance | raci
14 | Resources | Governance | resources
15 | Stakeholders | Governance | stakeholders
16 | Communications | Governance | communications
17 | Budget | Governance | budget
18 | Benefits | Governance | benefits
19 | Acceptance | Governance | acceptance
20 | Business Requirements | Requirements | business_requirements
21 | Functional Requirements | Requirements | functional_requirements
22 | Non-Functional Requirements | Requirements | non_functional_requirements
23 | Acceptance Criteria | Requirements | acceptance_criteria
24 | Traceability | Requirements | traceability
25 | ADR Register | Architecture | adrs
26 | Documentation | Architecture | documentation
27 | Architecture Components | Architecture | components
28 | Technologies | Architecture | technologies
29 | Integrations | Architecture | integrations
30 | APIs | Architecture | apis
31 | Environments | Architecture | environments
32 | Configuration | Architecture | configuration
33 | Data Assets | Data | data_assets
34 | Data Products | Data | data_products
35 | Data Contracts | Data | data_contracts
36 | Data Quality | Data | data_quality
37 | Classification | Data | data_classification
38 | Lineage | Data | lineage
39 | Retention | Data | retention
40 | AI Agents | AI | agents
41 | AI Models | AI | models
42 | AI RAG | AI | rag
43 | AI Evaluations | AI | ai_evaluations
44 | AI Provenance | AI | ai_provenance
45 | AI Authority | AI | ai_authority
46 | AI Risks | AI | ai_risks
47 | Security Controls | Security | security_controls
48 | Threat Register | Security | threats
49 | Vulnerabilities | Security | vulnerabilities
50 | Secrets Metadata | Security | secrets_metadata
51 | Certificates | Security | certificates
52 | Access Reviews | Security | access_reviews
53 | Compliance | Security | compliance
54 | Test Register | Delivery | tests
55 | Defects | Delivery | defects
56 | Evidence Register | Delivery | evidence
57 | Releases | Delivery | releases
58 | Deployments | Delivery | deployments
59 | CI and CD Controls | Delivery | cicd_controls
60 | Dependency Inventory | Delivery | dependencies_sbom
61 | Git Evidence | Delivery | git_evidence
62 | SLA and SLO | Operations | slos
63 | Capacity | Operations | capacity
64 | Monitoring | Operations | monitoring
65 | Incidents | Operations | incidents
66 | Problems and RCA | Operations | problems
67 | Runbooks | Operations | runbooks
68 | Backup and Restore | Operations | backup_restore
69 | Disaster Recovery | Operations | dr
70 | Training | Operations | training
71 | Change Log | Management | change_log
72 | Data Dictionary | Management | data_dictionary
How to read this workbook
1. Machine-managed columns (suffix M in the Data Dictionary) are regenerated on every update from repository evidence.
2. Human-controlled columns (H) are never modified by automation. They carry approvals, sign-offs, accepted risk and benefit acceptance.
3. EXISTS is not PASS: a PRESENT_EMPTY or NOT_RUN value is reported as such and never promoted to a pass.
4. Planned dates are planning baseline. Actual dates appear only where a record carries evidence.
5. Machine evidence never becomes human approval.
6. No secret value appears anywhere in this workbook.

## Executive Dashboard
Executive Dashboard
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Management summary generated from repository evidence. A number here is only as strong as the evidence behind it; gaps are stated, not smoothed over.
Overall RAG | GREY | Derived from task status, schedule variance and evidence state.
Programme progress | 0.0% | Weighted by planned duration. Evidence-weighted, not asserted.
Baseline start | 2026-08-01 | Baseline v1.0 - APPROVED_BASELINE. Planned dates are baseline dates, not actuals.
Days to baseline finish | 302 | Planning baseline finish. Not a forecast actual.
Repository HEAD | 24c8a1fd8845 | Branch main, 637 tracked files.
Last recorded test result | NOT_RUN | 97 suites discovered. Discovery is not a passing result.
dbt result | EMPTY_OUTPUT | manifest.json is PRESENT_EMPTY: the file exists but carries no result. EXISTS != PASS.
Terraform provisioning | CONTRACTS_ONLY | No resource or provider block is declared: Terraform defines governance contracts and provisions nothing yet.
Registers populated | 0 / 65 | Capability structure is defined for every register; a register with no records is AWAITING EVIDENCE / POPULATION.
Critical path and exceptions
Task ID | Title | Status | Planned finish | Variance (days) | RAG
No RED or AMBER tasks recorded

## Programme Dashboard
Programme Dashboard
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Delivery control view: phase progress, milestone position, register population and assurance state.
Phase progress
Phase | Name | Status | Planned start | Planned finish | % Complete | RAG
AWAITING POPULATION
Register population by capability
Register | Label | Records | Population state
acceptance | Acceptance and Sign-off | 0 | AWAITING EVIDENCE / POPULATION
acceptance_criteria | Acceptance Criteria | 0 | AWAITING EVIDENCE / POPULATION
access_reviews | Access Review Register | 0 | AWAITING EVIDENCE / POPULATION
adrs | ADR Register | 0 | AWAITING EVIDENCE / POPULATION
agents | Agent Register | 0 | AWAITING EVIDENCE / POPULATION
ai_authority | Delegated Authority Controls | 0 | AWAITING EVIDENCE / POPULATION
ai_evaluations | AI Evaluations | 0 | AWAITING EVIDENCE / POPULATION
ai_provenance | AI Provenance | 0 | AWAITING EVIDENCE / POPULATION
ai_risks | AI Risks | 0 | AWAITING EVIDENCE / POPULATION
apis | API Register | 0 | AWAITING EVIDENCE / POPULATION
backup_restore | Backup and Restore Register | 0 | AWAITING EVIDENCE / POPULATION
benefits | Benefits Realisation | 0 | AWAITING EVIDENCE / POPULATION
budget | Budget and Forecast | 0 | AWAITING EVIDENCE / POPULATION
business_requirements | Business Requirements | 0 | AWAITING EVIDENCE / POPULATION
capacity | Capacity and Performance Register | 0 | AWAITING EVIDENCE / POPULATION
certificates | Certificate Metadata Register | 0 | AWAITING EVIDENCE / POPULATION
change_requests | Change Requests | 0 | AWAITING EVIDENCE / POPULATION
cicd_controls | CI/CD Controls | 0 | AWAITING EVIDENCE / POPULATION
communications | Communications | 0 | AWAITING EVIDENCE / POPULATION
compliance | Compliance Mapping | 0 | AWAITING EVIDENCE / POPULATION
components | Architecture Components | 0 | AWAITING EVIDENCE / POPULATION
configuration | Configuration Register | 0 | AWAITING EVIDENCE / POPULATION
data_assets | Data Assets | 0 | AWAITING EVIDENCE / POPULATION
data_classification | Metadata and Classification | 0 | AWAITING EVIDENCE / POPULATION
data_contracts | Schema and Data Contract Register | 0 | AWAITING EVIDENCE / POPULATION
data_products | Data Product Catalogue | 0 | AWAITING EVIDENCE / POPULATION
data_quality | Data Quality Controls | 0 | AWAITING EVIDENCE / POPULATION
decisions | Decision Log | 0 | AWAITING EVIDENCE / POPULATION
defects | Defect Register | 0 | AWAITING EVIDENCE / POPULATION
deliverables | Deliverables | 0 | AWAITING EVIDENCE / POPULATION
dependencies | Dependencies | 0 | AWAITING EVIDENCE / POPULATION
dependencies_sbom | Dependency and SBOM Register | 0 | AWAITING EVIDENCE / POPULATION
deployments | Deployment Register | 0 | AWAITING EVIDENCE / POPULATION
dr | Disaster Recovery Register | 0 | AWAITING EVIDENCE / POPULATION
environments | Environment Register | 0 | AWAITING EVIDENCE / POPULATION
evidence | Evidence Register | 0 | AWAITING EVIDENCE / POPULATION
functional_requirements | Functional Requirements | 0 | AWAITING EVIDENCE / POPULATION
git_evidence | Git and Commit Evidence | 0 | AWAITING EVIDENCE / POPULATION
incidents | Incident Register | 0 | AWAITING EVIDENCE / POPULATION
integrations | Interface and Integration Register | 0 | AWAITING EVIDENCE / POPULATION
lineage | Lineage | 0 | AWAITING EVIDENCE / POPULATION
milestones | Milestones | 0 | AWAITING EVIDENCE / POPULATION
models | Model Register | 0 | AWAITING EVIDENCE / POPULATION
monitoring | Monitoring and Alert Register | 0 | AWAITING EVIDENCE / POPULATION
non_functional_requirements | Non-Functional Requirements | 0 | AWAITING EVIDENCE / POPULATION
phases | Phases | 0 | AWAITING EVIDENCE / POPULATION
problems | Problem and RCA Register | 0 | AWAITING EVIDENCE / POPULATION
raci | RACI | 0 | AWAITING EVIDENCE / POPULATION
rag | RAG and Retrieval Register | 0 | AWAITING EVIDENCE / POPULATION
raid | RAID | 0 | AWAITING EVIDENCE / POPULATION
releases | Release Register | 0 | AWAITING EVIDENCE / POPULATION
resources | Resources | 0 | AWAITING EVIDENCE / POPULATION
retention | Retention and Lifecycle | 0 | AWAITING EVIDENCE / POPULATION
runbooks | Runbook Register | 0 | AWAITING EVIDENCE / POPULATION
secrets_metadata | Secrets Metadata Register | 0 | AWAITING EVIDENCE / POPULATION
security_controls | Security Control Register | 0 | AWAITING EVIDENCE / POPULATION
slos | SLA / SLO / SLI Register | 0 | AWAITING EVIDENCE / POPULATION
stakeholders | Stakeholders | 0 | AWAITING EVIDENCE / POPULATION
tasks | Master Tasks (WBS) | 0 | AWAITING EVIDENCE / POPULATION
technologies | Technology Register | 0 | AWAITING EVIDENCE / POPULATION
tests | Test Register | 0 | AWAITING EVIDENCE / POPULATION
threats | Threat Register | 0 | AWAITING EVIDENCE / POPULATION
traceability | Requirements Traceability | 0 | AWAITING EVIDENCE / POPULATION
training | Training and Knowledge Transfer | 0 | AWAITING EVIDENCE / POPULATION
vulnerabilities | Vulnerability and Remediation Register | 0 | AWAITING EVIDENCE / POPULATION

## Master Tracker
Master Tracker
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
All WBS tasks ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Title | Phase ID | Owner | Status | Planned Start | Planned Finish | Actual Start | Actual Finish | Calculated Percent Complete | Calculated Schedule Variance Days | Calculated RAG | Calculated Days To Finish | Evidence Path | Requirement Ids | Component Ids | Control Ids | Test Ids | Dependencies | Notes
AWAITING POPULATION

## Gantt
Programme Timeline (Gantt)
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Planned baseline timeline at month granularity. Bars show PLANNED dates only. Cells are shaded green when evidenced progress has started and amber where the planned window has passed without completion. No actual date is inferred from this view.
ID | Title | Phase ID | Owner | Status | Planned Start | Planned Finish | Calculated Percent Complete | Calculated RAG | Aug 26 | Sep 26 | Oct 26 | Nov 26 | Dec 26 | Jan 27 | Feb 27 | Mar 27 | Apr 27 | May 27 | Jun 27 | Jul 27
AWAITING POPULATION

## Milestones
Milestones
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Programme milestones ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Phase ID | Criticality | Status | Planned Date | Forecast Date | Actual Date | Calculated RAG | Owner | Evidence Path | Notes
AWAITING POPULATION

## Phases
Phases
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Phases and gates ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Status | Planned Start | Planned Finish | Actual Start | Actual Finish | Owner | Calculated Percent Complete | Calculated RAG | Gate Criteria | Evidence Path | Notes
AWAITING POPULATION

## Deliverables
Deliverables
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Deliverables ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Phase ID | Owner | Status | Planned Start | Planned Finish | Calculated Percent Complete | Calculated RAG | Task Ids | Evidence Path | Acceptance State | Notes
AWAITING POPULATION

## Dependencies
Dependencies
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Dependencies ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Depends On | Type | Owner | Status | Predecessor ID | Successor ID | Target Date | Notes
AWAITING POPULATION

## RAID
RAID
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Risks, issues, assumptions, dependencies ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Type | Title | Severity | Status | Owner | Mitigation Task Ids | Control Ids | Probability | Impact | Raised Date | Due Date | Risk Acceptance | Residual Risk Acceptance | Evidence Path | Notes
AWAITING POPULATION

## Decision Log
Decision Log
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Programme and technical decisions ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Title | Decision Date | Status | Decider Role | Decision Rationale | Affected Scope | Evidence Path | Notes
AWAITING POPULATION

## Change Requests
Change Requests
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Change control ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Title | Raised Date | Status | Requester | Description | Impact | Decision Date | Evidence Path | Notes
AWAITING POPULATION

## RACI
RACI
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Role assignments ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Activity | Responsible | Accountable | Consulted | Informed
AWAITING POPULATION

## Resources
Resources
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Resources ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Role | Allocation Pct | Start Date | End Date | Notes
AWAITING POPULATION

## Stakeholders
Stakeholders
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Stakeholders ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Role | Engagement | Organisation | Notes
AWAITING POPULATION

## Communications
Communications
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Communications ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Channel | Audience | Cadence | Owner | Notes
AWAITING POPULATION

## Budget
Budget
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Budget and forecast ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Category | Basis | Currency | Approved Amount | Forecast Amount | Budget Approved | Budget Approver | Notes
AWAITING POPULATION

## Benefits
Benefits
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Benefits realisation ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Owner | Measurement | Status | Benefit Acceptance | Benefit Accepted By | Benefit Acceptance Date | Notes
AWAITING POPULATION

## Acceptance
Acceptance
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Acceptance and sign-off ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Subject | Decision | Decision Date | Conditions | Approver Role | Evidence Path | Notes
AWAITING POPULATION

## Business Requirements
Business Requirements
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Business requirements ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Title | Status | Description | Owner | Acceptance Criteria Ids | Evidence Path | Notes
AWAITING POPULATION

## Functional Requirements
Functional Requirements
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Functional requirements ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Title | Status | Business Requirement Ids | Description | Component Ids | Control Ids | Test Ids | Evidence Path | Notes
AWAITING POPULATION

## Non-Functional Requirements
Non-Functional Requirements
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Non-functional requirements ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Title | Category | Status | Business Requirement Ids | Target Metric | Control Ids | SLO Ids | Verified By | Evidence Path | Notes
AWAITING POPULATION

## Acceptance Criteria
Acceptance Criteria
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Acceptance criteria ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Requirement ID | Criterion | Evidence Required | Verification Method | Status | Evidence Path | Notes
AWAITING POPULATION

## Traceability
Traceability
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
End-to-end traceability ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Business Requirement ID | Functional Requirement Ids | Non Functional Requirement Ids | Component Ids | Adr Ids | Data Product Ids | Control Ids | Test Ids | Evidence Ids | Release Ids | SLO Ids | Runbook Ids | Acceptance Ids | Notes
AWAITING POPULATION

## ADR Register
ADR Register
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Architecture decision records ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Title | Status | Decision Date | Version | Location | Evidence Path | Decision Rationale | Notes
AWAITING POPULATION

## Documentation
Documentation
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Documentation inventory ¦ REGISTER 'documentation' IS NOT DEFINED
ID | Title | Location | Top Level | Document Date | Status | Bytes | Sha256 | Owner | Notes
AWAITING POPULATION

## Architecture Components
Architecture Components
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Components ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Category | Status | Technology Ids | Requirement Ids | Control Ids | Source Path | Notes
AWAITING POPULATION

## Technologies
Technologies
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Technology register ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Category | Status | Version | Source Path | Notes
AWAITING POPULATION

## Integrations
Integrations
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Interfaces and integrations ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Source Component | Target Component | Direction | Status | Protocol | Source Path | Notes
AWAITING POPULATION

## APIs
APIs
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
API register ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Path | Method | Owner Component | Status | Authentication | Source Path | Notes
AWAITING POPULATION

## Environments
Environments
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Environment register ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Classification | Status | Source Path | Notes
AWAITING POPULATION

## Configuration
Configuration
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Configuration register (metadata only) ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Location | Classification | Status | Owner | Notes
AWAITING POPULATION

## Data Assets
Data Assets
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Medallion data assets ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Layer | Status | Product Ids | Contract Ids | Control Ids | Source Path | Evidence Path | Notes
AWAITING POPULATION

## Data Products
Data Products
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Data product catalogue ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Audience | Status | Asset Ids | Contract Ids | Classification | Source Path | Evidence Path | Notes
AWAITING POPULATION

## Data Contracts
Data Contracts
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Schema and data contracts ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Kind | Location | Compatibility | Status | Contract Version | Sha256 | Notes
AWAITING POPULATION

## Data Quality
Data Quality
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Data quality controls ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Type | Dimension | Status | Asset ID | Rule Logic | Evidence Path | Notes
AWAITING POPULATION

## Classification
Classification
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Classification levels ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Level | Control | Retention Days | Masking Required | Evidence Path | Notes
AWAITING POPULATION

## Lineage
Lineage
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Dataset lineage ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Upstream | Downstream | Evidence Path | Notes
AWAITING POPULATION

## Retention
Retention
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Retention and lifecycle ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Asset Class | Retention Days | Enforcement Status | Evidence Path | Notes
AWAITING POPULATION

## AI Agents
AI Agents
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Agent register ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Capability | Status | Owner Component | Source Path | Test Ids | Evidence Path | Notes
AWAITING POPULATION

## AI Models
AI Models
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Model register ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Task | Status | Version | Metrics | Source Path | Evidence Path | Notes
AWAITING POPULATION

## AI RAG
AI RAG
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
RAG and retrieval ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Status | Backend | Source Path | Notes
AWAITING POPULATION

## AI Evaluations
AI Evaluations
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
AI evaluations ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Subject | Metric | Outcome | Observed On | Evidence Path | Notes
AWAITING POPULATION

## AI Provenance
AI Provenance
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
AI provenance ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Subject | Method | Status | Evidence Path | Notes
AWAITING POPULATION

## AI Authority
AI Authority
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Delegated authority controls ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Control Type | Enforcement | Source Path | Evidence Path | Notes
AWAITING POPULATION

## AI Risks
AI Risks
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
AI risks ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Title | Category | Severity | Status | Owner | Control Ids | Notes
AWAITING POPULATION

## Security Controls
Security Controls
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Security control register ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Title | Control Type | Implementation | Verification Status | Component Ids | Threat Ids | Test Ids | Source Path | Evidence Path | Notes
AWAITING POPULATION

## Threat Register
Threat Register
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Threat register ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Title | Category | Severity | Status | Control Ids | Evidence Path | Notes
AWAITING POPULATION

## Vulnerabilities
Vulnerabilities
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Vulnerability register ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Title | Severity | Status | Source | Remediation | Target Date | Evidence Path | Notes
AWAITING POPULATION

## Secrets Metadata
Secrets Metadata
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Secret metadata (never values) ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Owner | Provider | Status | Rotation Due | Last Rotated | Evidence Path | Notes
AWAITING POPULATION

## Certificates
Certificates
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Certificate metadata ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Subject | Purpose | Status | Valid From | Expires On | Notes
AWAITING POPULATION

## Access Reviews
Access Reviews
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Access reviews ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Scope | Review Type | Status | Reviewer Role | Last Reviewed | Next Due | Notes
AWAITING POPULATION

## Compliance
Compliance
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Compliance mapping ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Framework | Control Reference | Mapped Control Ids | Assessment Status | Evidence Path | Notes
AWAITING POPULATION

## Test Register
Test Register
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Test register ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Level | Scope | Status | Technical Status | Test Result | Test Count | Last Test Run | Requirement Ids | Source Path | Evidence Path | Notes
AWAITING POPULATION

## Defects
Defects
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Defects ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Title | Severity | Status | Raised Date | Owner | Component ID | Evidence Path | Notes
AWAITING POPULATION

## Evidence Register
Evidence Register
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Evidence ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Title | Evidence Type | Location | Status | Sha256 | Bytes | Observed At | Notes
AWAITING POPULATION

## Releases
Releases
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Releases ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Version | Status | Released On | Git SHA | Component Ids | Evidence Path | Notes
AWAITING POPULATION

## Deployments
Deployments
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Deployments ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Environment ID | Component ID | Status | Deployed On | Git SHA | Evidence Path | Notes
AWAITING POPULATION

## CI and CD Controls
CI and CD Controls
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
CI/CD controls ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Pipeline | Control Type | Status | Source Path | Evidence Path | Notes
AWAITING POPULATION

## Dependency Inventory
Dependency Inventory
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Declared dependencies and SBOM inputs ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Scope | Version Constraint | Status | Source Path | Notes
AWAITING POPULATION

## Git Evidence
Git Evidence
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Commit evidence ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | SHA | Summary | Author Date | Author | Evidence Path
AWAITING POPULATION

## SLA and SLO
SLA and SLO
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
SLA/SLO/SLI ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Sli Definition | Target | Status | Component Ids | Evidence Path | Notes
AWAITING POPULATION

## Capacity
Capacity
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Capacity and performance ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Subject | Metric | Design Target | Measured Value | Status | Evidence Path | Notes
AWAITING POPULATION

## Monitoring
Monitoring
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Monitoring and alerting ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Signal Type | Status | Source Path | Evidence Path | Notes
AWAITING POPULATION

## Incidents
Incidents
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Incidents ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Title | Severity | Status | Raised Date | Resolved On | Impact | Evidence Path | Notes
AWAITING POPULATION

## Problems and RCA
Problems and RCA
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Problem and RCA ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Title | Status | Root Cause | Corrective Action | Evidence Path | Notes
AWAITING POPULATION

## Runbooks
Runbooks
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Runbooks ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Scenario | Location | Owner | Last Tested | Notes
AWAITING POPULATION

## Backup and Restore
Backup and Restore
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Backup and restore ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Scope | Status | Last Tested | Rto | Rpo | Evidence Path | Notes
AWAITING POPULATION

## Disaster Recovery
Disaster Recovery
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Disaster recovery ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Name | Rto | Rpo | Status | Last Tested | Evidence Path | Notes
AWAITING POPULATION

## Training
Training
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Training and KT ¦ AWAITING EVIDENCE / POPULATION - 0 record(s); capability structure is defined but no evidence-backed records exist yet
ID | Topic | Audience | Status | Delivered On | Owner | Notes
AWAITING POPULATION

## Change Log
Refresh Change Summary
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
What this update changed relative to the previous workbook state. No record is ever silently deleted: a record that disappears from its register is retained here and flagged.
Change ID | Sheet / Register | Change type | Detail
CHG-001 | ADR Register | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-002 | AI Agents | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-003 | AI Authority | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-004 | AI Evaluations | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-005 | AI Models | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-006 | AI Provenance | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-007 | AI RAG | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-008 | AI Risks | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-009 | APIs | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-010 | Acceptance | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-011 | Acceptance Criteria | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-012 | Access Reviews | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-013 | Architecture Components | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-014 | Backup and Restore | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-015 | Benefits | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-016 | Budget | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-017 | Business Requirements | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-018 | CHG-001 | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-019 | CI and CD Controls | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-020 | Capacity | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-021 | Certificates | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-022 | Change Log | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-023 | Change Requests | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-024 | Classification | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-025 | Communications | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-026 | Compliance | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-027 | Configuration | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-028 | Data Assets | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-029 | Data Contracts | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-030 | Data Dictionary | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-031 | Data Products | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-032 | Data Quality | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-033 | Decision Log | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-034 | Defects | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-035 | Deliverables | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-036 | Dependencies | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-037 | Dependency Inventory | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-038 | Deployments | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-039 | Disaster Recovery | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-040 | Documentation | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-041 | Environments | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-042 | Evidence Register | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-043 | Functional Requirements | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-044 | Git Evidence | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-045 | Incidents | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-046 | Integrations | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-047 | Lineage | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-048 | Master Tracker | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-049 | Milestones | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-050 | Monitoring | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-051 | Non-Functional Requirements | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-052 | Phases | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-053 | Problems and RCA | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-054 | RACI | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-055 | RAID | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-056 | Releases | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-057 | Resources | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-058 | Retention | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-059 | Runbooks | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-060 | SLA and SLO | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-061 | Secrets Metadata | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-062 | Security Controls | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-063 | Stakeholders | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-064 | Technologies | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-065 | Test Register | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-066 | Threat Register | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-067 | Traceability | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-068 | Training | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-069 | Vulnerabilities | RETAINED_NOT_DELETED | This ID existed in the previous workbook but not in the current register. It was NOT silently deleted; review the register entry.
CHG-070 | workbook | REFRESH | Generated 2026-10-02T08:54:46+00:00 by tooling v1.0.0

## Data Dictionary
Data Dictionary and Field Ownership
DP AI Payments Platform Programme ¦ Baseline start 2026-08-01 ¦ Baseline v1.0 ¦ Refreshed 2026-10-02T08:54:46+00:00 ¦ Workbook v1.0.0
Every column used in this workbook, what it means, and who may change it. M = machine-managed, H = human-controlled, S = shared (human-seeded, machine-maintained).
Sheet | Column | Definition | Ownership
Master Tracker | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Master Tracker | title | Short human title of the record. | S - Shared (human-seeded)
Master Tracker | phase_id | Phase ID: register field. | H - Human-controlled
Master Tracker | owner | Accountable role or team (role-based, not personal data). | S - Shared (human-seeded)
Master Tracker | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Master Tracker | planned_start | PLANNING BASELINE start date. Not an actual date. | H - Human-controlled
Master Tracker | planned_finish | PLANNING BASELINE finish date. Not an actual date. | H - Human-controlled
Master Tracker | actual_start | Evidenced actual start. Blank when unevidenced; never invented. | H - Human-controlled
Master Tracker | actual_finish | Evidenced actual finish. Blank when unevidenced; never invented. | H - Human-controlled
Master Tracker | calculated_percent_complete | Machine-calculated, evidence-weighted percent complete. Weighted by planned duration. | M - Machine-managed
Master Tracker | calculated_schedule_variance_days | Machine-calculated days late against plan. Negative means ahead of plan. | M - Machine-managed
Master Tracker | calculated_rag | Machine-derived RAG from status, variance and evidence. A human override is held separately in manual_rag. | M - Machine-managed
Master Tracker | calculated_days_to_finish | Machine-calculated days from the refresh date to the planned finish. | M - Machine-managed
Master Tracker | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Master Tracker | requirement_ids | Requirement Ids: stable identifier(s) traced to another register. | H - Human-controlled
Master Tracker | component_ids | Component Ids: stable identifier(s) traced to another register. | H - Human-controlled
Master Tracker | control_ids | Control Ids: stable identifier(s) traced to another register. | H - Human-controlled
Master Tracker | test_ids | Test Ids: stable identifier(s) traced to another register. | H - Human-controlled
Master Tracker | dependencies | Dependencies: register field. | H - Human-controlled
Master Tracker | notes | Free-text context. Human-maintained. | H - Human-controlled
Milestones | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Milestones | name | Short human name of the record. | H - Human-controlled
Milestones | phase_id | Phase ID: register field. | H - Human-controlled
Milestones | criticality | Criticality: register field. | H - Human-controlled
Milestones | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Milestones | planned_date | Planned Date: register field. | H - Human-controlled
Milestones | forecast_date | Forecast Date: register field. | H - Human-controlled
Milestones | actual_date | Actual Date: register field. | H - Human-controlled
Milestones | calculated_rag | Machine-derived RAG from status, variance and evidence. A human override is held separately in manual_rag. | M - Machine-managed
Milestones | owner | Accountable role or team (role-based, not personal data). | S - Shared (human-seeded)
Milestones | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Milestones | notes | Free-text context. Human-maintained. | H - Human-controlled
Phases | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Phases | name | Short human name of the record. | H - Human-controlled
Phases | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Phases | planned_start | PLANNING BASELINE start date. Not an actual date. | H - Human-controlled
Phases | planned_finish | PLANNING BASELINE finish date. Not an actual date. | H - Human-controlled
Phases | actual_start | Evidenced actual start. Blank when unevidenced; never invented. | H - Human-controlled
Phases | actual_finish | Evidenced actual finish. Blank when unevidenced; never invented. | H - Human-controlled
Phases | owner | Accountable role or team (role-based, not personal data). | S - Shared (human-seeded)
Phases | calculated_percent_complete | Machine-calculated, evidence-weighted percent complete. Weighted by planned duration. | M - Machine-managed
Phases | calculated_rag | Machine-derived RAG from status, variance and evidence. A human override is held separately in manual_rag. | M - Machine-managed
Phases | gate_criteria | Gate Criteria: register field. | H - Human-controlled
Phases | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Phases | notes | Free-text context. Human-maintained. | H - Human-controlled
Deliverables | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Deliverables | name | Short human name of the record. | H - Human-controlled
Deliverables | phase_id | Phase ID: register field. | H - Human-controlled
Deliverables | owner | Accountable role or team (role-based, not personal data). | S - Shared (human-seeded)
Deliverables | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Deliverables | planned_start | PLANNING BASELINE start date. Not an actual date. | H - Human-controlled
Deliverables | planned_finish | PLANNING BASELINE finish date. Not an actual date. | H - Human-controlled
Deliverables | calculated_percent_complete | Machine-calculated, evidence-weighted percent complete. Weighted by planned duration. | M - Machine-managed
Deliverables | calculated_rag | Machine-derived RAG from status, variance and evidence. A human override is held separately in manual_rag. | M - Machine-managed
Deliverables | task_ids | Task Ids: stable identifier(s) traced to another register. | H - Human-controlled
Deliverables | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Deliverables | acceptance_state | Acceptance State: register field. | H - Human-controlled
Deliverables | notes | Free-text context. Human-maintained. | H - Human-controlled
Dependencies | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Dependencies | name | Short human name of the record. | H - Human-controlled
Dependencies | depends_on | Depends On: register field. | H - Human-controlled
Dependencies | type | Type: register field. | H - Human-controlled
Dependencies | owner | Accountable role or team (role-based, not personal data). | S - Shared (human-seeded)
Dependencies | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Dependencies | predecessor_id | Predecessor ID: register field. | H - Human-controlled
Dependencies | successor_id | Successor ID: register field. | H - Human-controlled
Dependencies | target_date | Target Date: register field. | H - Human-controlled
Dependencies | notes | Free-text context. Human-maintained. | H - Human-controlled
RAID | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
RAID | type | Type: register field. | H - Human-controlled
RAID | title | Short human title of the record. | S - Shared (human-seeded)
RAID | severity | Impact classification from the register's closed vocabulary. | M - Machine-managed
RAID | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
RAID | owner | Accountable role or team (role-based, not personal data). | S - Shared (human-seeded)
RAID | mitigation_task_ids | Mitigation Task Ids: stable identifier(s) traced to another register. | H - Human-controlled
RAID | control_ids | Control Ids: stable identifier(s) traced to another register. | H - Human-controlled
RAID | probability | Probability: register field. | H - Human-controlled
RAID | impact | Impact: register field. | H - Human-controlled
RAID | raised_date | Raised Date: register field. | H - Human-controlled
RAID | due_date | Due Date: register field. | H - Human-controlled
RAID | risk_acceptance | HUMAN residual-risk acceptance decision. Automation never writes it. | H - Human-controlled
RAID | residual_risk_acceptance | HUMAN residual-risk acceptance after mitigation. | H - Human-controlled
RAID | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
RAID | notes | Free-text context. Human-maintained. | H - Human-controlled
Decision Log | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Decision Log | title | Short human title of the record. | S - Shared (human-seeded)
Decision Log | decision_date | Decision Date: register field. | H - Human-controlled
Decision Log | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Decision Log | decider_role | Decider Role: register field. | H - Human-controlled
Decision Log | decision_rationale | Decision Rationale: register field. | H - Human-controlled
Decision Log | affected_scope | Affected Scope: register field. | H - Human-controlled
Decision Log | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Decision Log | notes | Free-text context. Human-maintained. | H - Human-controlled
Change Requests | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Change Requests | title | Short human title of the record. | S - Shared (human-seeded)
Change Requests | raised_date | Raised Date: register field. | H - Human-controlled
Change Requests | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Change Requests | requester | Requester: register field. | H - Human-controlled
Change Requests | description | What the record covers. | S - Shared (human-seeded)
Change Requests | impact | Impact: register field. | H - Human-controlled
Change Requests | decision_date | Decision Date: register field. | H - Human-controlled
Change Requests | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Change Requests | notes | Free-text context. Human-maintained. | H - Human-controlled
RACI | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
RACI | activity | Activity: register field. | H - Human-controlled
RACI | responsible | Responsible: register field. | H - Human-controlled
RACI | accountable | Accountable: register field. | H - Human-controlled
RACI | consulted | Consulted: register field. | H - Human-controlled
RACI | informed | Informed: register field. | H - Human-controlled
Resources | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Resources | name | Short human name of the record. | H - Human-controlled
Resources | role | Role: register field. | H - Human-controlled
Resources | allocation_pct | Allocation Pct: register field. | H - Human-controlled
Resources | start_date | Start Date: register field. | H - Human-controlled
Resources | end_date | End Date: register field. | H - Human-controlled
Resources | notes | Free-text context. Human-maintained. | H - Human-controlled
Stakeholders | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Stakeholders | name | Short human name of the record. | H - Human-controlled
Stakeholders | role | Role: register field. | H - Human-controlled
Stakeholders | engagement | Engagement: register field. | H - Human-controlled
Stakeholders | organisation | Organisation: register field. | H - Human-controlled
Stakeholders | notes | Free-text context. Human-maintained. | H - Human-controlled
Communications | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Communications | channel | Channel: register field. | H - Human-controlled
Communications | audience | Audience: register field. | H - Human-controlled
Communications | cadence | Cadence: register field. | H - Human-controlled
Communications | owner | Accountable role or team (role-based, not personal data). | S - Shared (human-seeded)
Communications | notes | Free-text context. Human-maintained. | H - Human-controlled
Budget | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Budget | category | Category: register field. | M - Machine-managed
Budget | basis | Basis: register field. | H - Human-controlled
Budget | currency | Currency: register field. | H - Human-controlled
Budget | approved_amount | Approved Amount: register field. | H - Human-controlled
Budget | forecast_amount | Forecast Amount: register field. | H - Human-controlled
Budget | budget_approved | HUMAN budget approval. Automation never writes it. | H - Human-controlled
Budget | budget_approver | Budget Approver: register field. | H - Human-controlled
Budget | notes | Free-text context. Human-maintained. | H - Human-controlled
Benefits | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Benefits | name | Short human name of the record. | H - Human-controlled
Benefits | owner | Accountable role or team (role-based, not personal data). | S - Shared (human-seeded)
Benefits | measurement | Measurement: register field. | H - Human-controlled
Benefits | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Benefits | benefit_acceptance | HUMAN benefit acceptance. Automation never writes it. | H - Human-controlled
Benefits | benefit_accepted_by | Benefit Accepted By: register field. | H - Human-controlled
Benefits | benefit_acceptance_date | Benefit Acceptance Date: register field. | H - Human-controlled
Benefits | notes | Free-text context. Human-maintained. | H - Human-controlled
Acceptance | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Acceptance | subject | Subject: register field. | H - Human-controlled
Acceptance | decision | Decision: register field. | H - Human-controlled
Acceptance | decision_date | Decision Date: register field. | H - Human-controlled
Acceptance | conditions | Conditions: register field. | H - Human-controlled
Acceptance | approver_role | Approver Role: register field. | H - Human-controlled
Acceptance | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Acceptance | notes | Free-text context. Human-maintained. | H - Human-controlled
Business Requirements | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Business Requirements | title | Short human title of the record. | S - Shared (human-seeded)
Business Requirements | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Business Requirements | description | What the record covers. | S - Shared (human-seeded)
Business Requirements | owner | Accountable role or team (role-based, not personal data). | S - Shared (human-seeded)
Business Requirements | acceptance_criteria_ids | Acceptance Criteria Ids: stable identifier(s) traced to another register. | H - Human-controlled
Business Requirements | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Business Requirements | notes | Free-text context. Human-maintained. | H - Human-controlled
Functional Requirements | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Functional Requirements | title | Short human title of the record. | S - Shared (human-seeded)
Functional Requirements | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Functional Requirements | business_requirement_ids | Business Requirement Ids: stable identifier(s) traced to another register. | H - Human-controlled
Functional Requirements | description | What the record covers. | S - Shared (human-seeded)
Functional Requirements | component_ids | Component Ids: stable identifier(s) traced to another register. | H - Human-controlled
Functional Requirements | control_ids | Control Ids: stable identifier(s) traced to another register. | H - Human-controlled
Functional Requirements | test_ids | Test Ids: stable identifier(s) traced to another register. | H - Human-controlled
Functional Requirements | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Functional Requirements | notes | Free-text context. Human-maintained. | H - Human-controlled
Non-Functional Requirements | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Non-Functional Requirements | title | Short human title of the record. | S - Shared (human-seeded)
Non-Functional Requirements | category | Category: register field. | M - Machine-managed
Non-Functional Requirements | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Non-Functional Requirements | business_requirement_ids | Business Requirement Ids: stable identifier(s) traced to another register. | H - Human-controlled
Non-Functional Requirements | target_metric | Target Metric: register field. | H - Human-controlled
Non-Functional Requirements | control_ids | Control Ids: stable identifier(s) traced to another register. | H - Human-controlled
Non-Functional Requirements | slo_ids | SLO Ids: stable identifier(s) traced to another register. | H - Human-controlled
Non-Functional Requirements | verified_by | Verified By: register field. | H - Human-controlled
Non-Functional Requirements | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Non-Functional Requirements | notes | Free-text context. Human-maintained. | H - Human-controlled
Acceptance Criteria | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Acceptance Criteria | requirement_id | Requirement ID: register field. | H - Human-controlled
Acceptance Criteria | criterion | Criterion: register field. | H - Human-controlled
Acceptance Criteria | evidence_required | Evidence Required: register field. | H - Human-controlled
Acceptance Criteria | verification_method | Verification Method: register field. | H - Human-controlled
Acceptance Criteria | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Acceptance Criteria | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Acceptance Criteria | notes | Free-text context. Human-maintained. | H - Human-controlled
Traceability | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Traceability | business_requirement_id | Business Requirement ID: register field. | H - Human-controlled
Traceability | functional_requirement_ids | Functional Requirement Ids: stable identifier(s) traced to another register. | H - Human-controlled
Traceability | non_functional_requirement_ids | Non Functional Requirement Ids: stable identifier(s) traced to another register. | H - Human-controlled
Traceability | component_ids | Component Ids: stable identifier(s) traced to another register. | H - Human-controlled
Traceability | adr_ids | Adr Ids: stable identifier(s) traced to another register. | H - Human-controlled
Traceability | data_product_ids | Data Product Ids: stable identifier(s) traced to another register. | H - Human-controlled
Traceability | control_ids | Control Ids: stable identifier(s) traced to another register. | H - Human-controlled
Traceability | test_ids | Test Ids: stable identifier(s) traced to another register. | H - Human-controlled
Traceability | evidence_ids | Evidence Ids: stable identifier(s) traced to another register. | H - Human-controlled
Traceability | release_ids | Release Ids: stable identifier(s) traced to another register. | H - Human-controlled
Traceability | slo_ids | SLO Ids: stable identifier(s) traced to another register. | H - Human-controlled
Traceability | runbook_ids | Runbook Ids: stable identifier(s) traced to another register. | H - Human-controlled
Traceability | acceptance_ids | Acceptance Ids: stable identifier(s) traced to another register. | H - Human-controlled
Traceability | notes | Free-text context. Human-maintained. | H - Human-controlled
ADR Register | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
ADR Register | title | Short human title of the record. | S - Shared (human-seeded)
ADR Register | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
ADR Register | decision_date | Decision Date: register field. | H - Human-controlled
ADR Register | version | Version: register field. | S - Shared (human-seeded)
ADR Register | location | Repository path of the referenced artefact. | H - Human-controlled
ADR Register | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
ADR Register | decision_rationale | Decision Rationale: register field. | H - Human-controlled
ADR Register | notes | Free-text context. Human-maintained. | H - Human-controlled
Documentation | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Documentation | title | Short human title of the record. | S - Shared (human-seeded)
Documentation | location | Repository path of the referenced artefact. | H - Human-controlled
Documentation | top_level | Top Level: register field. | H - Human-controlled
Documentation | document_date | Document Date: register field. | H - Human-controlled
Documentation | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Documentation | bytes | Size in bytes. A zero-byte artefact is PRESENT_EMPTY, not a pass. | H - Human-controlled
Documentation | sha256 | Content hash of the referenced artefact. | H - Human-controlled
Documentation | owner | Accountable role or team (role-based, not personal data). | S - Shared (human-seeded)
Documentation | notes | Free-text context. Human-maintained. | H - Human-controlled
Architecture Components | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Architecture Components | name | Short human name of the record. | H - Human-controlled
Architecture Components | category | Category: register field. | M - Machine-managed
Architecture Components | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Architecture Components | technology_ids | Technology Ids: stable identifier(s) traced to another register. | H - Human-controlled
Architecture Components | requirement_ids | Requirement Ids: stable identifier(s) traced to another register. | H - Human-controlled
Architecture Components | control_ids | Control Ids: stable identifier(s) traced to another register. | H - Human-controlled
Architecture Components | source_path | Source Path: register field. | M - Machine-managed
Architecture Components | notes | Free-text context. Human-maintained. | H - Human-controlled
Technologies | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Technologies | name | Short human name of the record. | H - Human-controlled
Technologies | category | Category: register field. | M - Machine-managed
Technologies | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Technologies | version | Version: register field. | S - Shared (human-seeded)
Technologies | source_path | Source Path: register field. | M - Machine-managed
Technologies | notes | Free-text context. Human-maintained. | H - Human-controlled
Integrations | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Integrations | name | Short human name of the record. | H - Human-controlled
Integrations | source_component | Source Component: register field. | H - Human-controlled
Integrations | target_component | Target Component: register field. | H - Human-controlled
Integrations | direction | Direction: register field. | H - Human-controlled
Integrations | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Integrations | protocol | Protocol: register field. | H - Human-controlled
Integrations | source_path | Source Path: register field. | M - Machine-managed
Integrations | notes | Free-text context. Human-maintained. | H - Human-controlled
APIs | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
APIs | path | Path: register field. | H - Human-controlled
APIs | method | Method: register field. | H - Human-controlled
APIs | owner_component | Owner Component: register field. | H - Human-controlled
APIs | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
APIs | authentication | Authentication: register field. | H - Human-controlled
APIs | source_path | Source Path: register field. | M - Machine-managed
APIs | notes | Free-text context. Human-maintained. | H - Human-controlled
Environments | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Environments | name | Short human name of the record. | H - Human-controlled
Environments | classification | Data or environment classification level. | H - Human-controlled
Environments | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Environments | source_path | Source Path: register field. | M - Machine-managed
Environments | notes | Free-text context. Human-maintained. | H - Human-controlled
Configuration | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Configuration | name | Short human name of the record. | H - Human-controlled
Configuration | location | Repository path of the referenced artefact. | H - Human-controlled
Configuration | classification | Data or environment classification level. | H - Human-controlled
Configuration | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Configuration | owner | Accountable role or team (role-based, not personal data). | S - Shared (human-seeded)
Configuration | notes | Free-text context. Human-maintained. | H - Human-controlled
Data Assets | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Data Assets | name | Short human name of the record. | H - Human-controlled
Data Assets | layer | Layer: register field. | H - Human-controlled
Data Assets | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Data Assets | product_ids | Product Ids: stable identifier(s) traced to another register. | H - Human-controlled
Data Assets | contract_ids | Contract Ids: stable identifier(s) traced to another register. | H - Human-controlled
Data Assets | control_ids | Control Ids: stable identifier(s) traced to another register. | H - Human-controlled
Data Assets | source_path | Source Path: register field. | M - Machine-managed
Data Assets | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Data Assets | notes | Free-text context. Human-maintained. | H - Human-controlled
Data Products | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Data Products | name | Short human name of the record. | H - Human-controlled
Data Products | audience | Audience: register field. | H - Human-controlled
Data Products | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Data Products | asset_ids | Asset Ids: stable identifier(s) traced to another register. | H - Human-controlled
Data Products | contract_ids | Contract Ids: stable identifier(s) traced to another register. | H - Human-controlled
Data Products | classification | Data or environment classification level. | H - Human-controlled
Data Products | source_path | Source Path: register field. | M - Machine-managed
Data Products | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Data Products | notes | Free-text context. Human-maintained. | H - Human-controlled
Data Contracts | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Data Contracts | name | Short human name of the record. | H - Human-controlled
Data Contracts | kind | Kind: register field. | H - Human-controlled
Data Contracts | location | Repository path of the referenced artefact. | H - Human-controlled
Data Contracts | compatibility | Compatibility: register field. | H - Human-controlled
Data Contracts | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Data Contracts | contract_version | Contract Version: register field. | M - Machine-managed
Data Contracts | sha256 | Content hash of the referenced artefact. | H - Human-controlled
Data Contracts | notes | Free-text context. Human-maintained. | H - Human-controlled
Data Quality | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Data Quality | name | Short human name of the record. | H - Human-controlled
Data Quality | type | Type: register field. | H - Human-controlled
Data Quality | dimension | Dimension: register field. | H - Human-controlled
Data Quality | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Data Quality | asset_id | Asset ID: register field. | H - Human-controlled
Data Quality | rule_logic | Rule Logic: register field. | H - Human-controlled
Data Quality | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Data Quality | notes | Free-text context. Human-maintained. | H - Human-controlled
Classification | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Classification | name | Short human name of the record. | H - Human-controlled
Classification | level | Level: register field. | H - Human-controlled
Classification | control | Control: register field. | H - Human-controlled
Classification | retention_days | Retention Days: register field. | H - Human-controlled
Classification | masking_required | Masking Required: register field. | H - Human-controlled
Classification | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Classification | notes | Free-text context. Human-maintained. | H - Human-controlled
Lineage | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Lineage | name | Short human name of the record. | H - Human-controlled
Lineage | upstream | Upstream: register field. | H - Human-controlled
Lineage | downstream | Downstream: register field. | H - Human-controlled
Lineage | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Lineage | notes | Free-text context. Human-maintained. | H - Human-controlled
Retention | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Retention | name | Short human name of the record. | H - Human-controlled
Retention | asset_class | Asset Class: register field. | H - Human-controlled
Retention | retention_days | Retention Days: register field. | H - Human-controlled
Retention | enforcement_status | Enforcement Status: register field. | H - Human-controlled
Retention | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Retention | notes | Free-text context. Human-maintained. | H - Human-controlled
AI Agents | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
AI Agents | name | Short human name of the record. | H - Human-controlled
AI Agents | capability | Capability: register field. | H - Human-controlled
AI Agents | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
AI Agents | owner_component | Owner Component: register field. | H - Human-controlled
AI Agents | source_path | Source Path: register field. | M - Machine-managed
AI Agents | test_ids | Test Ids: stable identifier(s) traced to another register. | H - Human-controlled
AI Agents | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
AI Agents | notes | Free-text context. Human-maintained. | H - Human-controlled
AI Models | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
AI Models | name | Short human name of the record. | H - Human-controlled
AI Models | task | Task: register field. | H - Human-controlled
AI Models | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
AI Models | version | Version: register field. | S - Shared (human-seeded)
AI Models | metrics | Metrics: register field. | H - Human-controlled
AI Models | source_path | Source Path: register field. | M - Machine-managed
AI Models | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
AI Models | notes | Free-text context. Human-maintained. | H - Human-controlled
AI RAG | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
AI RAG | name | Short human name of the record. | H - Human-controlled
AI RAG | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
AI RAG | backend | Backend: register field. | H - Human-controlled
AI RAG | source_path | Source Path: register field. | M - Machine-managed
AI RAG | notes | Free-text context. Human-maintained. | H - Human-controlled
AI Evaluations | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
AI Evaluations | subject | Subject: register field. | H - Human-controlled
AI Evaluations | metric | Metric: register field. | H - Human-controlled
AI Evaluations | outcome | Outcome: register field. | H - Human-controlled
AI Evaluations | observed_on | Observed On: register field. | H - Human-controlled
AI Evaluations | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
AI Evaluations | notes | Free-text context. Human-maintained. | H - Human-controlled
AI Provenance | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
AI Provenance | subject | Subject: register field. | H - Human-controlled
AI Provenance | method | Method: register field. | H - Human-controlled
AI Provenance | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
AI Provenance | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
AI Provenance | notes | Free-text context. Human-maintained. | H - Human-controlled
AI Authority | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
AI Authority | name | Short human name of the record. | H - Human-controlled
AI Authority | control_type | Control Type: register field. | H - Human-controlled
AI Authority | enforcement | Enforcement: register field. | H - Human-controlled
AI Authority | source_path | Source Path: register field. | M - Machine-managed
AI Authority | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
AI Authority | notes | Free-text context. Human-maintained. | H - Human-controlled
AI Risks | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
AI Risks | title | Short human title of the record. | S - Shared (human-seeded)
AI Risks | category | Category: register field. | M - Machine-managed
AI Risks | severity | Impact classification from the register's closed vocabulary. | M - Machine-managed
AI Risks | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
AI Risks | owner | Accountable role or team (role-based, not personal data). | S - Shared (human-seeded)
AI Risks | control_ids | Control Ids: stable identifier(s) traced to another register. | H - Human-controlled
AI Risks | notes | Free-text context. Human-maintained. | H - Human-controlled
Security Controls | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Security Controls | title | Short human title of the record. | S - Shared (human-seeded)
Security Controls | control_type | Control Type: register field. | H - Human-controlled
Security Controls | implementation | Whether the control is implemented, partially implemented, designed or absent. | H - Human-controlled
Security Controls | verification_status | How a control was proven. VERIFIED_RUNTIME is distinct from DOCUMENTED_ONLY. | H - Human-controlled
Security Controls | component_ids | Component Ids: stable identifier(s) traced to another register. | H - Human-controlled
Security Controls | threat_ids | Threat Ids: stable identifier(s) traced to another register. | H - Human-controlled
Security Controls | test_ids | Test Ids: stable identifier(s) traced to another register. | H - Human-controlled
Security Controls | source_path | Source Path: register field. | M - Machine-managed
Security Controls | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Security Controls | notes | Free-text context. Human-maintained. | H - Human-controlled
Threat Register | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Threat Register | title | Short human title of the record. | S - Shared (human-seeded)
Threat Register | category | Category: register field. | M - Machine-managed
Threat Register | severity | Impact classification from the register's closed vocabulary. | M - Machine-managed
Threat Register | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Threat Register | control_ids | Control Ids: stable identifier(s) traced to another register. | H - Human-controlled
Threat Register | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Threat Register | notes | Free-text context. Human-maintained. | H - Human-controlled
Vulnerabilities | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Vulnerabilities | title | Short human title of the record. | S - Shared (human-seeded)
Vulnerabilities | severity | Impact classification from the register's closed vocabulary. | M - Machine-managed
Vulnerabilities | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Vulnerabilities | source | Source: register field. | H - Human-controlled
Vulnerabilities | remediation | Remediation: register field. | H - Human-controlled
Vulnerabilities | target_date | Target Date: register field. | H - Human-controlled
Vulnerabilities | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Vulnerabilities | notes | Free-text context. Human-maintained. | H - Human-controlled
Secrets Metadata | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Secrets Metadata | name | Short human name of the record. | H - Human-controlled
Secrets Metadata | owner | Accountable role or team (role-based, not personal data). | S - Shared (human-seeded)
Secrets Metadata | provider | Provider: register field. | H - Human-controlled
Secrets Metadata | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Secrets Metadata | rotation_due | Rotation Due: register field. | H - Human-controlled
Secrets Metadata | last_rotated | Last Rotated: register field. | H - Human-controlled
Secrets Metadata | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Secrets Metadata | notes | Free-text context. Human-maintained. | H - Human-controlled
Certificates | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Certificates | name | Short human name of the record. | H - Human-controlled
Certificates | subject | Subject: register field. | H - Human-controlled
Certificates | purpose | Purpose: register field. | H - Human-controlled
Certificates | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Certificates | valid_from | Valid From: register field. | H - Human-controlled
Certificates | expires_on | Expires On: register field. | H - Human-controlled
Certificates | notes | Free-text context. Human-maintained. | H - Human-controlled
Access Reviews | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Access Reviews | scope | Scope: register field. | H - Human-controlled
Access Reviews | review_type | Review Type: register field. | H - Human-controlled
Access Reviews | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Access Reviews | reviewer_role | Reviewer Role: register field. | H - Human-controlled
Access Reviews | last_reviewed | Last Reviewed: register field. | H - Human-controlled
Access Reviews | next_due | Next Due: register field. | H - Human-controlled
Access Reviews | notes | Free-text context. Human-maintained. | H - Human-controlled
Compliance | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Compliance | framework | Framework: register field. | H - Human-controlled
Compliance | control_reference | Control Reference: register field. | H - Human-controlled
Compliance | mapped_control_ids | Mapped Control Ids: stable identifier(s) traced to another register. | H - Human-controlled
Compliance | assessment_status | Assessment Status: register field. | H - Human-controlled
Compliance | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Compliance | notes | Free-text context. Human-maintained. | H - Human-controlled
Test Register | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Test Register | name | Short human name of the record. | H - Human-controlled
Test Register | level | Level: register field. | H - Human-controlled
Test Register | scope | Scope: register field. | H - Human-controlled
Test Register | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Test Register | technical_status | Machine-observed technical state, for example DISCOVERED or CONTRACT_ONLY. | M - Machine-managed
Test Register | test_result | Last recorded machine test result. NOT_RUN means no result is recorded, which is not a pass. | M - Machine-managed
Test Register | test_count | Machine-counted tests in the referenced suite. | M - Machine-managed
Test Register | last_test_run | Last Test Run: register field. | M - Machine-managed
Test Register | requirement_ids | Requirement Ids: stable identifier(s) traced to another register. | H - Human-controlled
Test Register | source_path | Source Path: register field. | M - Machine-managed
Test Register | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Test Register | notes | Free-text context. Human-maintained. | H - Human-controlled
Defects | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Defects | title | Short human title of the record. | S - Shared (human-seeded)
Defects | severity | Impact classification from the register's closed vocabulary. | M - Machine-managed
Defects | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Defects | raised_date | Raised Date: register field. | H - Human-controlled
Defects | owner | Accountable role or team (role-based, not personal data). | S - Shared (human-seeded)
Defects | component_id | Component ID: register field. | H - Human-controlled
Defects | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Defects | notes | Free-text context. Human-maintained. | H - Human-controlled
Evidence Register | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Evidence Register | title | Short human title of the record. | S - Shared (human-seeded)
Evidence Register | evidence_type | Evidence Type: register field. | M - Machine-managed
Evidence Register | location | Repository path of the referenced artefact. | H - Human-controlled
Evidence Register | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Evidence Register | sha256 | Content hash of the referenced artefact. | H - Human-controlled
Evidence Register | bytes | Size in bytes. A zero-byte artefact is PRESENT_EMPTY, not a pass. | H - Human-controlled
Evidence Register | observed_at | Observed At: register field. | H - Human-controlled
Evidence Register | notes | Free-text context. Human-maintained. | H - Human-controlled
Releases | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Releases | name | Short human name of the record. | H - Human-controlled
Releases | version | Version: register field. | S - Shared (human-seeded)
Releases | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Releases | released_on | Released On: register field. | H - Human-controlled
Releases | git_sha | Machine-captured Git commit SHA. | M - Machine-managed
Releases | component_ids | Component Ids: stable identifier(s) traced to another register. | H - Human-controlled
Releases | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Releases | notes | Free-text context. Human-maintained. | H - Human-controlled
Deployments | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Deployments | environment_id | Environment ID: register field. | H - Human-controlled
Deployments | component_id | Component ID: register field. | H - Human-controlled
Deployments | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Deployments | deployed_on | Deployed On: register field. | H - Human-controlled
Deployments | git_sha | Machine-captured Git commit SHA. | M - Machine-managed
Deployments | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Deployments | notes | Free-text context. Human-maintained. | H - Human-controlled
CI and CD Controls | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
CI and CD Controls | name | Short human name of the record. | H - Human-controlled
CI and CD Controls | pipeline | Pipeline: register field. | H - Human-controlled
CI and CD Controls | control_type | Control Type: register field. | H - Human-controlled
CI and CD Controls | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
CI and CD Controls | source_path | Source Path: register field. | M - Machine-managed
CI and CD Controls | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
CI and CD Controls | notes | Free-text context. Human-maintained. | H - Human-controlled
Dependency Inventory | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Dependency Inventory | name | Short human name of the record. | H - Human-controlled
Dependency Inventory | scope | Scope: register field. | H - Human-controlled
Dependency Inventory | version_constraint | Version Constraint: register field. | H - Human-controlled
Dependency Inventory | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Dependency Inventory | source_path | Source Path: register field. | M - Machine-managed
Dependency Inventory | notes | Free-text context. Human-maintained. | H - Human-controlled
Git Evidence | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Git Evidence | sha | SHA: register field. | H - Human-controlled
Git Evidence | summary | Summary: register field. | H - Human-controlled
Git Evidence | author_date | Author Date: register field. | H - Human-controlled
Git Evidence | author | Author: register field. | H - Human-controlled
Git Evidence | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
SLA and SLO | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
SLA and SLO | name | Short human name of the record. | H - Human-controlled
SLA and SLO | sli_definition | Sli Definition: register field. | H - Human-controlled
SLA and SLO | target | Target: register field. | H - Human-controlled
SLA and SLO | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
SLA and SLO | component_ids | Component Ids: stable identifier(s) traced to another register. | H - Human-controlled
SLA and SLO | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
SLA and SLO | notes | Free-text context. Human-maintained. | H - Human-controlled
Capacity | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Capacity | subject | Subject: register field. | H - Human-controlled
Capacity | metric | Metric: register field. | H - Human-controlled
Capacity | design_target | Design Target: register field. | H - Human-controlled
Capacity | measured_value | Measured Value: register field. | H - Human-controlled
Capacity | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Capacity | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Capacity | notes | Free-text context. Human-maintained. | H - Human-controlled
Monitoring | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Monitoring | name | Short human name of the record. | H - Human-controlled
Monitoring | signal_type | Signal Type: register field. | H - Human-controlled
Monitoring | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Monitoring | source_path | Source Path: register field. | M - Machine-managed
Monitoring | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Monitoring | notes | Free-text context. Human-maintained. | H - Human-controlled
Incidents | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Incidents | title | Short human title of the record. | S - Shared (human-seeded)
Incidents | severity | Impact classification from the register's closed vocabulary. | M - Machine-managed
Incidents | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Incidents | raised_date | Raised Date: register field. | H - Human-controlled
Incidents | resolved_on | Resolved On: register field. | H - Human-controlled
Incidents | impact | Impact: register field. | H - Human-controlled
Incidents | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Incidents | notes | Free-text context. Human-maintained. | H - Human-controlled
Problems and RCA | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Problems and RCA | title | Short human title of the record. | S - Shared (human-seeded)
Problems and RCA | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Problems and RCA | root_cause | Root Cause: register field. | H - Human-controlled
Problems and RCA | corrective_action | Corrective Action: register field. | H - Human-controlled
Problems and RCA | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Problems and RCA | notes | Free-text context. Human-maintained. | H - Human-controlled
Runbooks | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Runbooks | name | Short human name of the record. | H - Human-controlled
Runbooks | scenario | Scenario: register field. | H - Human-controlled
Runbooks | location | Repository path of the referenced artefact. | H - Human-controlled
Runbooks | owner | Accountable role or team (role-based, not personal data). | S - Shared (human-seeded)
Runbooks | last_tested | Last Tested: register field. | H - Human-controlled
Runbooks | notes | Free-text context. Human-maintained. | H - Human-controlled
Backup and Restore | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Backup and Restore | name | Short human name of the record. | H - Human-controlled
Backup and Restore | scope | Scope: register field. | H - Human-controlled
Backup and Restore | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Backup and Restore | last_tested | Last Tested: register field. | H - Human-controlled
Backup and Restore | rto | Rto: register field. | H - Human-controlled
Backup and Restore | rpo | Rpo: register field. | H - Human-controlled
Backup and Restore | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Backup and Restore | notes | Free-text context. Human-maintained. | H - Human-controlled
Disaster Recovery | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Disaster Recovery | name | Short human name of the record. | H - Human-controlled
Disaster Recovery | rto | Rto: register field. | H - Human-controlled
Disaster Recovery | rpo | Rpo: register field. | H - Human-controlled
Disaster Recovery | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Disaster Recovery | last_tested | Last Tested: register field. | H - Human-controlled
Disaster Recovery | evidence_path | Repository path holding the supporting evidence. | M - Machine-managed
Disaster Recovery | notes | Free-text context. Human-maintained. | H - Human-controlled
Training | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Training | topic | Topic: register field. | H - Human-controlled
Training | audience | Audience: register field. | H - Human-controlled
Training | status | Current lifecycle state, from the register's closed vocabulary. | S - Shared (human-seeded)
Training | delivered_on | Delivered On: register field. | H - Human-controlled
Training | owner | Accountable role or team (role-based, not personal data). | S - Shared (human-seeded)
Training | notes | Free-text context. Human-maintained. | H - Human-controlled
Change Log | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Change Log | sheet | Sheet: register field. | H - Human-controlled
Change Log | change_type | Change Type: register field. | H - Human-controlled
Change Log | record_id | Record ID: register field. | H - Human-controlled
Change Log | detail | Detail: register field. | H - Human-controlled
Data Dictionary | id | Stable record identifier. Never reused, never renumbered. | S - Shared (human-seeded)
Data Dictionary | sheet | Sheet: register field. | H - Human-controlled
Data Dictionary | column | Column: register field. | H - Human-controlled
Data Dictionary | definition | Definition: register field. | H - Human-controlled
Data Dictionary | ownership | Ownership: register field. | H - Human-controlled